## Sheet1
Project Timeline and Presentation Structure | [7 empty] | PowerPoint Presentation Structure
Slide Number | Phase | Task | Start Date | End Date | Duration | Section | Content Description |  | Slide Number | Section | Content Description
1 | Research and Planning | Identify literature | 2024-09-23 | 2024-09-24 | 1 day | Title Slide | Project Title, Your Name, Course/Date |  | 1 | Title Slide | Title: "Fraud Detection in Online Consumer Reviews Using Machine Learning Techniques"
2 |  | Define project goals | 2024-09-25 | 2024-09-26 | 2 days | Business Problem | Define the business challenge; use statistics or examples to illustrate its importance |  | 2 | Business Problem | Discuss the impact of fraudulent reviews on businesses and consumers; include relevant statistics and examples.
3 | Data Collection | Gather datasets | 2024-09-27 | 2024-10-02 | 5 days | Data Science Problem | Translate the business problem into a specific data science problem; state the objective |  | 3 | Data Science Problem | Define the specific problem of identifying fraudulent reviews using natural language processing (NLP).
4 |  | Clean and organize data | 2024-10-03 | 2024-10-06 | 4 days | Stakeholders | Identify key stakeholders and discuss their benefits from project outcomes |  | 4 | Stakeholders | Identify stakeholders: e-commerce platforms, consumers, businesses, regulatory agencies, and data scientists.
5 | Model Development | Choose algorithms | 2024-10-07 | 2024-10-09 | 3 days | Dataset | Overview of the dataset(s) used, including source, size, and notable features |  | 5 | Dataset | Overview of the dataset: Describe Amazon's labeled dataset with verified purchase labels, size, features, and preprocessing steps.
6 |  | Train models | 2024-10-10 | 2024-10-12 | 3 days | Exploratory Data Analysis (EDA) | Highlight key findings with visuals; discuss distributions, correlations, and interesting patterns |  | 6 | Exploratory Data Analysis (EDA) | Present visualizations of review distributions, sentiment analysis, and key insights from the dataset.
7 | Evaluation | Test model | 2024-10-13 | 2024-10-13 | 1 day | Models | List selected algorithms/models; explain reasons for their selection |  | 7 | Models | Discuss the selected classifiers: Multinomial Naive Bayes (MNB), Support Vector Machine (SVM), and Logistic Regression (LR); rationale for their selection.
8 |  |  | 2024-10-14 | 2024-10-14 | 1 day | Evaluation and Comparison | Describe evaluation metrics; present model performance comparison using visuals |  | 8 | Evaluation and Comparison | Describe evaluation metrics (accuracy, precision, recall); compare model performance using Count Vectorizer vs. TF-IDF Vectorizer.
9 |  |  | 2024-10-15 | 2024-10-15 | 1 day | Results | Summarize main findings; use visuals to illustrate key results and implications |  | 9 | Results | Highlight the performance of the best model (e.g., LR with 85% accuracy and 92% recall); include key metrics and visuals.
10 |  |  | 2024-10-16 | 2024-10-19 | 4 days | Conclusion / Future Work | Recap overall findings; discuss potential future directions and improvements |  | 10 | Conclusion / Future Work | Summarize key findings, discuss limitations, and suggest future directions for enhancing the model or exploring new techniques.